| Key Milestone | Deadline for 04/16/2014 admin | Client Obligations |
| --- | --- | --- |
| Complete Test Center Intake Form | 11/22/13 | Client is responsible for compiling accurate contact information for all proposed test center locations, including designated Test Center Supervisor, and confirming Enrollment on the Test Center Intake Form provided by the College Board. Test Center Intake Forms must be complete before Test Center Master Forms are distributed to the test center locations. |
| Online Course welcome kit delivery | 40 Days from the Receipt of the Completed Test Center Intake Form | Client will ensure timely distribution of the online course access codes and other information provided by the College Board to the Enrolled Students. Client is responsible for promoting usage of the Online Course. |
| Establish Test Centers | 01/20/14 | The designated Test Center Supervisor at each participating school will complete a Test Center Master Form provided by the College Board and return it in accordance with the instructions on the form. This form is required to recognize the school as a Test Center for the Program and enable shipment of test materials to the Test Center. Compliance is required for all participating schools, even those who are currently registered as test centers for National SAT Administrations. |
| Application for accommodations for Participants with disabilities | 02/26/14 | Client will ensure timely application by all Enrolled Students requesting College Board approved accommodations in accordance with the terms outlined in Schedule 1. |
| Registration start date | 02/05/14 | Client will ensure compliance with all registration procedures in accordance with the terms outlined in Schedule 1 and this Attachment. |
| Registration end date | 04/02/14 | Client will ensure compliance with all registration procedures in accordance with the terms outlined in Schedule 1 and this Attachment. |
| Test Center Supervisor Training | 04/02/14 | Client will ensure compliance with all Test Center Supervisor Training requirements in accordance with the terms outlined in Schedule 1. |
| SAT School Day Test Administration | 04/16/14 | Client will ensure all personnel facilities and logistics are in place for a successful test administration in accordance with the terms outlined in Schedule 1. |